## Gantt Chart
Task | Assignee | Status | Feb 25, 2025 | Feb 26, 2025 | Feb 27, 2025 | Feb 28, 2025 | Mar 01, 2025 | Mar 02, 2025 | Mar 03, 2025 | Mar 04, 2025 | Mar 05, 2025 | Mar 06, 2025 | Mar 07, 2025 | Mar 08, 2025 | Mar 09, 2025 | Mar 10, 2025 | Mar 11, 2025 | Mar 12, 2025 | Mar 13, 2025 | Mar 14, 2025 | Mar 15, 2025 | Mar 16, 2025 | Mar 17, 2025 | Mar 18, 2025 | Mar 19, 2025 | Mar 20, 2025 | Mar 21, 2025 | Mar 22, 2025 | Mar 23, 2025 | Mar 24, 2025 | Mar 25, 2025 | Mar 26, 2025 | Mar 27, 2025 | Mar 28, 2025 | Mar 29, 2025 | Mar 30, 2025 | Mar 31, 2025 | Apr 01, 2025 | Apr 02, 2025 | Apr 03, 2025 | Apr 04, 2025 | Apr 05, 2025 | Apr 06, 2025 | Apr 07, 2025 | Apr 08, 2025 | Apr 09, 2025 | Apr 10, 2025 | Apr 11, 2025 | Apr 12, 2025 | Apr 13, 2025 | Apr 14, 2025 | Apr 15, 2025 | Apr 16, 2025 | Apr 17, 2025 | Apr 18, 2025 | Apr 19, 2025 | Apr 20, 2025 | Apr 21, 2025 | Apr 22, 2025 | Apr 23, 2025 | Apr 24, 2025 | Apr 25, 2025 | Apr 26, 2025 | Apr 27, 2025 | Apr 28, 2025 | Apr 29, 2025 | Apr 30, 2025 | May 01, 2025 | May 02, 2025 | May 03, 2025 | May 04, 2025 | May 05, 2025 | May 06, 2025 | May 07, 2025 | May 08, 2025 | May 09, 2025 | May 10, 2025 | May 11, 2025 | May 12, 2025 | May 13, 2025 | May 14, 2025 | May 15, 2025
Requirement Gathering/Analysis |  | Done | █ | █ | █ | █ | █ | █ | █
Identifying Stakeholders | Bhaskar Reddy | Done | Identified who would be the end users
Collecting Requirements | Owen Trombly | Done | Setup meeting with the users and collected the initial requirements
Categorizing Requirements | Ashik Ahmed | Done | Post meeting figured out platform selection
Documentation of Initial Requirements | Bhakti Shetty | Done | Proposed initial document with user specified requirement
Documentation of Final Requirements | Ankit Mhadye | Done | Proposed final version of document with architectural design, front end and back end technologies, database to be used and milestones to be achieved
Design |  | Done | [7 empty] | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █
High Level Design | Bhakti Shetty, Ankit Mhadye, Ashik Ahmed | Done | [7 empty] | Created architectural design, system design and ER model using Lucid chart
Low Level Design | Ankit Mhadye, Owen Trombly, Bhaskar Reddy | Done | [7 empty] | Created Database schema and table design using Erwin
Spring Break |  | Done | [18 empty] | █ | █ | █ | █ | █ | █ | █ | █ | █
Initial Backend | Bhakti Shetty, Ankit Mhadye | Done | [18 empty] | Created database and tables for Booking Site Aggregator and also finalized the tables
Initial Frontend | Ankit Mhadye, Owen Trombly, Bhaskar Reddy, Ashik Ahmed | Done | [18 empty] | Created front end design using Angular
Development | Unassigned | To Do | [27 empty] | █ | █ | █ | █ | █ | █ | █ | █
Initial Build Setup | Unassigned | To Do
Database setup and creation | Unassigned | To Do
Build and Unit Test: Python | Unassigned | To Do
Build and Unit Test: Angular | Unassigned | To Do
UI/UX design | Unassigned | To Do | [27 empty] | █ | █ | █ | █ | █ | █ | █
UI/UX functionality | Unassigned | To Do | [34 empty] | █ | █ | █ | █ | █ | █ | █
front end database integrations | Unassigned | To Do | [35 empty] | █ | █ | █ | █ | █ | █ | █
backend database integrations | Unassigned | To Do | [35 empty] | █ | █ | █ | █ | █ | █ | █ | █
front end testing | Unassigned | To Do | [43 empty] | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █
backend testing | Unassigned | To Do | [43 empty] | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █
Deployment | Unassigned | To Do | [50 empty] | █ | █ | █ | █ | █ | █ | █
final review of project | Unassigned | To Do | [57 empty] | █ | █ | █ | █ | █ | █ | █

## Timeline Analysis
Metric | Value
Total Tasks | 24
Average Task Duration (Days) | 11.31
Task Status Breakdown
To Do | 15
Done | 9
Task Distribution by Assignee
Ankit Mhadye | 5
Owen Trombly | 3
Ashik Ahmed | 3
Bhakti Shetty | 3
Bhaskar Reddy | 3